STRIKEEDGE

Development Plan

Strike-Level Technical Analysis Platform for Indian Options

Version 1.0 | March 2026

28-Week Development Timeline

# Development Phases Overview

| Phase | Duration | Focus | Key Deliverable |
| --- | --- | --- | --- |
| 1 | Weeks 1-4 | Data Pipeline & Indicators | RSI on strike charts |
| 2 | Weeks 5-8 | Screener Engine & UI | Working web screener |
| 3 | Weeks 9-12 | Options Data & Filters | IV, Greeks, OI filtering |
| 4 | Weeks 13-16 | User System | Auth, saved scans, alerts |
| 5 | Weeks 17-22 | AI/ML & Marketplace | Pattern recognition, sharing |
| 6 | Weeks 23-28 | Mobile & Production | iOS/Android apps, launch |

# Phase 1: Foundation & Data Pipeline

Weeks 1-4 | Goal: Prove the concept works

## Week 1: Project Setup & Angel One Integration

| Day | Tasks | Deliverables |
| --- | --- | --- |
| 1 | Create GitHub repo, project structure, Docker Compose | strikeedge/ with Redis, PostgreSQL, TimescaleDB |
| 2 | Angel One authentication with TOTP | Working login, session management |
| 2-3 | Scrip master loader | All NFO instruments in database |
| 3 | Filter for options | CE/PE strikes with tokens |

## Week 2: Historical Candle Pipeline

| Day | Tasks | Deliverables |
| --- | --- | --- |
| 1 | Historical candle API wrapper | Fetch 5-min candles for any strike |
| 2 | TimescaleDB schema design | Hypertable for OHLCV data |
| 3 | Candle storage pipeline | Store 50 candles per strike |
| 4-5 | Batch fetcher | History for all active strikes |

## Week 3: Real-Time Candle Builder

| Day | Tasks | Deliverables |
| --- | --- | --- |
| 1-2 | WebSocket connection to Angel One | Subscribe to tick feed |
| 2-3 | Redis candle aggregator | Build candles from ticks in memory |
| 4 | Candle completion handler | Push to TimescaleDB on close |
| 5 | Testing & validation | Compare with Angel One historical |

## Week 4: Basic Indicator Engine

| Day | Tasks | Deliverables |
| --- | --- | --- |
| 1 | RSI calculation | RSI(14) on strike candles |
| 2 | MACD calculation | MACD(12,26,9) on strike candles |
| 3 | EMA/SMA | Moving averages |
| 4 | Indicator engine class | Compute all indicators |
| 5 | Validation | Compare RSI with TradingView |

### Phase 1 Success Criteria

- Fetch scrip master and identify all NIFTY option strikes

- Get historical 5-minute candles for NIFTY 24000 CE

- Compute RSI(14) on those candles

- Compare with TradingView — variance < 0.5%

# Phase 2: Screener Engine & Basic UI

Weeks 5-8 | Goal: Working screener with web interface

## Week 5: Signal Detection

- Crossover detection: RSI crosses above/below threshold

- Threshold events: Value enters/exits range

- State tracking: Store previous values per strike

- Event queue: Push detected signals to processing

## Week 6: FastAPI Backend

| Endpoint | Method | Description |
| --- | --- | --- |
| /api/instruments | GET | List all F&O underlyings |
| /api/strikes/{underlying} | GET | Get active strikes for underlying |
| /api/scan | POST | Create and run a scan |
| /api/scan/{id}/results | GET | Get scan results (WebSocket) |
| /api/chart/{token} | GET | Get OHLCV + indicators for strike |

## Week 7-8: React Frontend

| Component | Features |
| --- | --- |
| ScreenerBuilder | Configure indicator + condition + threshold value |
| UnderlyingSelector | Pick stocks/indexes to include in scan |
| ResultsTable | Live updating table of matching strikes |
| ChartViewer | TradingView Lightweight Charts with indicators |

### Phase 2 Success Criteria

- User can select indicator, condition, and value

- Scan runs and returns matching strikes

- Results update in real-time via WebSocket

- Click any result to see strike chart with indicators

# Phase 3: Options Data & Advanced Filters

Weeks 9-12 | Goal: Full options analytics

## Greeks & IV Implementation

| Metric | Library | Calculation Method |
| --- | --- | --- |
| Implied Volatility | py_vollib | Newton-Raphson from option price |
| Delta | mibian | Black-Scholes first derivative |
| Gamma | mibian | Black-Scholes second derivative |
| Theta | mibian | Time decay calculation |
| Vega | mibian | Volatility sensitivity |

## OI & Volume Analysis

- OI Change: Current vs previous day open interest

- OI % Change: Percentage change in OI

- Volume Spike: Current volume vs 20-day average

- Put/Call Ratio: PCR by OI and by volume

## Multi-Condition Screener

Enable complex queries combining all three dimensions:

- Strike Technicals: RSI > 60 on the strike's own chart

- Options Metrics: IV > 20% AND OI change > 10%

- Underlying: Spot above 200 EMA

# Phases 4-6: Summary

## Phase 4: User System (Weeks 13-16)

- Clerk authentication (email + Google OAuth)

- Save/load screener configurations

- Alert system (email + push notifications)

- Watchlists and favorite strikes

## Phase 5: AI/ML & Marketplace (Weeks 17-22)

- Pattern recognition ML model (candlestick, chart patterns)

- Sentiment analysis from news and social media

- Strategy marketplace for publishing/sharing screeners

- Performance tracking and ratings

## Phase 6: Mobile & Production (Weeks 23-28)

- React Native app (iOS + Android)

- AWS production deployment (ECS, Aurora, ElastiCache)

- Load testing and security audit

- Beta launch with 100 users

# Infrastructure & Environments

## Local Development

| Component | Setup |
| --- | --- |
| Services | Docker Compose (Redis, PostgreSQL, TimescaleDB) |
| API | FastAPI with hot reload (uvicorn --reload) |
| Frontend | Next.js/Vite dev server |
| Data | Angel One sandbox/paper trading |

## Production (AWS)

| Service | Configuration |
| --- | --- |
| Compute | ECS Fargate with auto-scaling |
| Database | Aurora Serverless v2 (0.5-2 ACU) |
| Cache | ElastiCache Redis Cluster |
| CDN | CloudFront for static assets |
| API | API Gateway with throttling |
| Monitoring | CloudWatch, X-Ray |

# Cost Estimates

## Development Phase (Months 1-6)

| Item | Monthly | Notes |
| --- | --- | --- |
| Local Docker | ₹0 | Free |
| Angel One API | ₹0 | Free tier |
| AWS Staging | ₹3,000-5,000 | Minimal setup |
| Total | ₹3,000-5,000 | ~$40-60 |

## Production (At Scale)

| Service | Monthly | Notes |
| --- | --- | --- |
| ECS Fargate | ₹8,000-15,000 | Auto-scaling |
| Aurora Serverless | ₹4,000-8,000 | 0.5-2 ACU |
| ElastiCache Redis | ₹5,000-10,000 | Cluster |
| Other (CDN, API GW) | ₹3,000-7,000 | Traffic-based |
| Total | ₹25,000-50,000 | ~$300-600 |

# Immediate Next Steps

Actions for Week 1:

## Day 1: Project Setup

- Create GitHub repository: strikeedge

- Set up project structure (backend/, frontend/, terraform/)

- Create docker-compose.yml for local services

- Initialize Python project with uv

## Day 2-3: Angel One Integration

- Create backend/data_pipeline/angel_one.py

- Implement TOTP authentication

- Fetch and parse scrip master JSON

- Filter for NFO options, store in database

## Day 4-5: First Indicator

- Fetch 5-minute candles for NIFTY 24000 CE

- Implement RSI(14) calculation

- Compare result with TradingView

- Document any variance and adjust

Week 1 Success: RSI(14) on NIFTY 24000 CE with < 0.5% variance vs TradingView

Ready to build! 🚀