## Dashboard
STRIKEEDGE PROJECT TRACKER
Enterprise Development Tracking System
PROJECT INFORMATION
Project Name: | StrikeEdge Options Screener | Project Manager:
Start Date: |  | Target End Date:
Current Phase: |  | Overall Status:
Last Updated: | 2026-03-08 | Next Milestone:
PHASE SUMMARY
Phase | Name | Weeks | Total Tasks | Completed | In Progress | Blocked | % Complete | Status
0 | Environment Setup | Pre | 25 | 0 | 0 | 0
1 | Foundation & Data Pipeline | 1-4 | 85 | 0 | 0 | 0
2 | Screener Engine & UI | 5-8 | 72 | 0 | 0 | 0
3 | Options Data & Filters | 9-12 | 68 | 0 | 0 | 0
4 | User System | 13-16 | 58 | 0 | 0 | 0
5 | AI Agents | 17-22 | 95 | 0 | 0 | 0
6 | Mobile & Production | 23-28 | 82 | 0 | 0 | 0
TOTAL
KEY METRICS
Total Tasks |  |  | Days Elapsed | 0 |  |  |  |  | 1
Tasks Completed |  |  | Days Remaining | 0
Tasks In Progress |  |  | Velocity (tasks/week) | [6 empty] | 1
Tasks Blocked |  |  | Est. Completion
STATUS LEGEND
⬜ | Not Started
🟡 | In Progress
✅ | Complete
❌ | Blocked
⏸️ | On Hold

## Phase 0 - Setup
PHASE 0: ENVIRONMENT SETUP
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
0.1.1 | Install Python 3.12+ | Dev Tools | P0 | ⬜ |  |  |  |  | - | Download from python.org
0.1.2 | Install uv package manager | Dev Tools | P0 | ⬜ |  |  |  |  | 0.1.1 | curl -LsSf https://astral.sh/uv/install.sh ¦ sh
0.1.3 | Verify uv installation | Dev Tools | P0 | ⬜ |  |  |  |  | 0.1.2 | uv --version
0.1.4 | Install Node.js 20+ | Dev Tools | P0 | ⬜ |  |  |  |  | - | Download LTS from nodejs.org
0.1.5 | Verify Node installation | Dev Tools | P0 | ⬜ |  |  |  |  | 0.1.4 | node --version
0.1.6 | Install Git | Dev Tools | P0 | ⬜ |  |  |  |  | -
0.1.7 | Install VS Code/Cursor IDE | Dev Tools | P1 | ⬜ |  |  |  |  | -
0.1.8 | Install Python extension | Dev Tools | P1 | ⬜ |  |  |  |  | 0.1.7
0.1.9 | Install Pylance extension | Dev Tools | P1 | ⬜ |  |  |  |  | 0.1.7
0.2.1 | Download Ollama | Ollama | P0 | ⬜ |  |  |  |  | - | https://ollama.ai
0.2.2 | Install Ollama | Ollama | P0 | ⬜ |  |  |  |  | 0.2.1
0.2.3 | Start Ollama service | Ollama | P0 | ⬜ |  |  |  |  | 0.2.2 | ollama serve
0.2.4 | Pull Llama3.2 model | Ollama | P0 | ⬜ |  |  |  |  | 0.2.3 | ollama pull llama3.2 (~3GB)
0.2.5 | Pull embedding model | Ollama | P0 | ⬜ |  |  |  |  | 0.2.3 | ollama pull nomic-embed-text
0.2.6 | Test Ollama | Ollama | P0 | ⬜ |  |  |  |  | 0.2.4 | ollama run llama3.2 'Hello'
0.2.7 | Verify models list | Ollama | P0 | ⬜ |  |  |  |  | 0.2.5 | ollama list
0.3.1 | Create Angel One account | Angel One | P0 | ⬜ |  |  |  |  | - | If not exists
0.3.2 | Enable API access | Angel One | P0 | ⬜ |  |  |  |  | 0.3.1 | In Angel One settings
0.3.3 | Get API Key | Angel One | P0 | ⬜ |  |  |  |  | 0.3.2 | Save securely
0.3.4 | Get Client ID | Angel One | P0 | ⬜ |  |  |  |  | 0.3.2
0.3.5 | Set up TOTP authenticator | Angel One | P0 | ⬜ |  |  |  |  | 0.3.2 | Google Authenticator
0.3.6 | Get TOTP Secret | Angel One | P0 | ⬜ |  |  |  |  | 0.3.5 | For automated login
0.3.7 | Test login via app | Angel One | P0 | ⬜ |  |  |  |  | 0.3.6
0.3.8 | Document credentials | Angel One | P0 | ⬜ |  |  |  |  | 0.3.7 | In password manager
0.4.1 | Create project directory | Project | P0 | ⬜ |  |  |  |  | - | mkdir strikeedge

## Phase 1 - Data
PHASE 1: FOUNDATION & DATA PIPELINE (Weeks 1-4)
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
1.1.1 | Create database/models.py | Database | P0 | ⬜ |  |  |  |  | - | SQLAlchemy models
1.1.2 | Define Instrument model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.3 | Define Candle model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.4 | Define IndicatorValue model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.5 | Define Screener model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.6 | Define ScanResult model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.7 | Define AgentJob model | Database | P0 | ⬜ |  |  |  |  | 1.1.1
1.1.8 | Create init_db.py | Database | P0 | ⬜ |  |  |  |  | 1.1.7
1.1.9 | Run database initialization | Database | P0 | ⬜ |  |  |  |  | 1.1.8
1.1.10 | Verify SQLite created | Database | P0 | ⬜ |  |  |  |  | 1.1.9
1.1.11 | Test insert instrument | Database | P1 | ⬜ |  |  |  |  | 1.1.10 | Unit test
1.1.12 | Test query instruments | Database | P1 | ⬜ |  |  |  |  | 1.1.11 | Unit test
1.2.1 | Create cache/file_cache.py | Cache | P0 | ⬜ |  |  |  |  | -
1.2.2 | Implement FileCache class | Cache | P0 | ⬜ |  |  |  |  | 1.2.1
1.2.3 | Implement set() with TTL | Cache | P0 | ⬜ |  |  |  |  | 1.2.2
1.2.4 | Implement get() | Cache | P0 | ⬜ |  |  |  |  | 1.2.2
1.2.5 | Implement delete() | Cache | P0 | ⬜ |  |  |  |  | 1.2.2
1.2.6 | Write cache unit tests | Cache | P1 | ⬜ |  |  |  |  | 1.2.5
1.3.1 | Create data_pipeline/angel_one.py | Angel One | P0 | ⬜ |  |  |  |  | -
1.3.2 | Install SmartAPI library | Angel One | P0 | ⬜ |  |  |  |  | 1.3.1 | uv add smartapi-python
1.3.3 | Implement AngelOneClient class | Angel One | P0 | ⬜ |  |  |  |  | 1.3.2
1.3.4 | Implement TOTP generation | Angel One | P0 | ⬜ |  |  |  |  | 1.3.3
1.3.5 | Implement authenticate() | Angel One | P0 | ⬜ |  |  |  |  | 1.3.4
1.3.6 | Test authentication | Angel One | P0 | ⬜ |  |  |  |  | 1.3.5 | Must succeed
1.3.7 | Handle auth errors | Angel One | P1 | ⬜ |  |  |  |  | 1.3.6
1.3.8 | Store session in cache | Angel One | P1 | ⬜ |  |  |  |  | 1.3.6
1.4.1 | Implement fetch_scrip_master() | Scrip Master | P0 | ⬜ |  |  |  |  | 1.3.6
1.4.2 | Parse scrip master JSON | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.1
1.4.3 | Filter NFO segment | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.2
1.4.4 | Filter OPTIDX instruments | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.3
1.4.5 | Filter OPTSTK instruments | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.3
1.4.6 | Extract token, symbol, strike | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.5
1.4.7 | Store instruments in DB | Scrip Master | P0 | ⬜ |  |  |  |  | 1.4.6
1.4.8 | Test: Count instruments | Scrip Master | P1 | ⬜ |  |  |  |  | 1.4.7
1.4.9 | Test: Query NIFTY options | Scrip Master | P1 | ⬜ |  |  |  |  | 1.4.7
1.4.10 | Test: Query BANKNIFTY | Scrip Master | P1 | ⬜ |  |  |  |  | 1.4.7
1.5.1 | Create candle_fetcher.py | Candles | P0 | ⬜ |  |  |  |  | 1.3.6
1.5.2 | Implement CandleFetcher class | Candles | P0 | ⬜ |  |  |  |  | 1.5.1
1.5.3 | Implement fetch_historical() | Candles | P0 | ⬜ |  |  |  |  | 1.5.2
1.5.4 | Support 1min timeframe | Candles | P0 | ⬜ |  |  |  |  | 1.5.3
1.5.5 | Support 5min timeframe | Candles | P0 | ⬜ |  |  |  |  | 1.5.3
1.5.6 | Support 15min timeframe | Candles | P0 | ⬜ |  |  |  |  | 1.5.3
1.5.7 | Handle pagination | Candles | P0 | ⬜ |  |  |  |  | 1.5.3 | Max 500/request
1.5.8 | Parse to DataFrame | Candles | P0 | ⬜ |  |  |  |  | 1.5.7
1.5.9 | Test: Fetch NIFTY spot | Candles | P1 | ⬜ |  |  |  |  | 1.5.8
1.5.10 | Test: Fetch strike candles | Candles | P1 | ⬜ |  |  |  |  | 1.5.8
1.6.1 | Implement store_candles() | Storage | P0 | ⬜ |  |  |  |  | 1.5.8
1.6.2 | Implement get_candles() | Storage | P0 | ⬜ |  |  |  |  | 1.6.1
1.6.3 | Implement get_latest_candle() | Storage | P0 | ⬜ |  |  |  |  | 1.6.1
1.6.4 | Add DB indexes | Storage | P0 | ⬜ |  |  |  |  | 1.6.3
1.6.5 | Test: Store 50 candles | Storage | P1 | ⬜ |  |  |  |  | 1.6.4
1.6.6 | Test: Retrieve by date range | Storage | P1 | ⬜ |  |  |  |  | 1.6.5
1.7.1 | Create batch_fetcher.py | Batch | P0 | ⬜ |  |  |  |  | 1.6.4
1.7.2 | Implement rate limiting | Batch | P0 | ⬜ |  |  |  |  | 1.7.1 | 2 req/sec
1.7.3 | Add progress bar (rich) | Batch | P1 | ⬜ |  |  |  |  | 1.7.2
1.7.4 | Implement retry logic | Batch | P0 | ⬜ |  |  |  |  | 1.7.2
1.7.5 | Test: Fetch 10 strikes | Batch | P1 | ⬜ |  |  |  |  | 1.7.4
1.7.6 | Test: Fetch all NIFTY | Batch | P1 | ⬜ |  |  |  |  | 1.7.5
1.8.1 | Create websocket_client.py | WebSocket | P0 | ⬜ |  |  |  |  | 1.3.6
1.8.2 | Implement WS connection | WebSocket | P0 | ⬜ |  |  |  |  | 1.8.1
1.8.3 | Handle reconnection | WebSocket | P0 | ⬜ |  |  |  |  | 1.8.2
1.8.4 | Subscribe to tick feed | WebSocket | P0 | ⬜ |  |  |  |  | 1.8.3
1.8.5 | Parse tick messages | WebSocket | P0 | ⬜ |  |  |  |  | 1.8.4
1.8.6 | Test: Receive ticks | WebSocket | P1 | ⬜ |  |  |  |  | 1.8.5
1.9.1 | Create tick_handler.py | Ticks | P0 | ⬜ |  |  |  |  | 1.8.5
1.9.2 | Implement TickHandler class | Ticks | P0 | ⬜ |  |  |  |  | 1.9.1
1.9.3 | Store ticks in buffer | Ticks | P0 | ⬜ |  |  |  |  | 1.9.2
1.9.4 | Group by strike token | Ticks | P0 | ⬜ |  |  |  |  | 1.9.3
1.9.5 | Test: Process 1000 ticks | Ticks | P1 | ⬜ |  |  |  |  | 1.9.4
1.10.1 | Create candle_builder.py | Builder | P0 | ⬜ |  |  |  |  | 1.9.4
1.10.2 | Implement CandleBuilder | Builder | P0 | ⬜ |  |  |  |  | 1.10.1
1.10.3 | Build OHLCV from ticks | Builder | P0 | ⬜ |  |  |  |  | 1.10.2
1.10.4 | Support multi-timeframe | Builder | P0 | ⬜ |  |  |  |  | 1.10.3
1.10.5 | Detect candle completion | Builder | P0 | ⬜ |  |  |  |  | 1.10.4
1.10.6 | Test: Build 1min candles | Builder | P1 | ⬜ |  |  |  |  | 1.10.5
1.10.7 | Test: Build 5min candles | Builder | P1 | ⬜ |  |  |  |  | 1.10.5
1.11.1 | Create indicators/rsi.py | RSI | P0 | ⬜ |  |  |  |  | 1.6.4
1.11.2 | Implement RSI calculation | RSI | P0 | ⬜ |  |  |  |  | 1.11.1
1.11.3 | Support configurable period | RSI | P0 | ⬜ |  |  |  |  | 1.11.2 | Default 14
1.11.4 | Test: RSI sample data | RSI | P1 | ⬜ |  |  |  |  | 1.11.3
1.11.5 | Validate vs TradingView | RSI | P0 | ⬜ |  |  |  |  | 1.11.4 | < 0.5% variance
1.12.1 | Create indicators/macd.py | MACD | P0 | ⬜ |  |  |  |  | 1.11.5
1.12.2 | Implement MACD line | MACD | P0 | ⬜ |  |  |  |  | 1.12.1 | 12,26 EMA
1.12.3 | Implement signal line | MACD | P0 | ⬜ |  |  |  |  | 1.12.2 | 9 EMA
1.12.4 | Implement histogram | MACD | P0 | ⬜ |  |  |  |  | 1.12.3
1.12.5 | Test: MACD sample data | MACD | P1 | ⬜ |  |  |  |  | 1.12.4
1.13.1 | Create indicators/ema.py | EMA | P0 | ⬜ |  |  |  |  | 1.12.5
1.13.2 | Implement EMA calculation | EMA | P0 | ⬜ |  |  |  |  | 1.13.1
1.13.3 | Support multiple periods | EMA | P0 | ⬜ |  |  |  |  | 1.13.2 | 9,20,50,200
1.14.1 | Create indicators/bollinger.py | Bollinger | P1 | ⬜ |  |  |  |  | 1.13.3
1.14.2 | Implement BB calculation | Bollinger | P1 | ⬜ |  |  |  |  | 1.14.1
1.15.1 | Create indicators/engine.py | Engine | P0 | ⬜ |  |  |  |  | 1.14.2
1.15.2 | Implement IndicatorEngine | Engine | P0 | ⬜ |  |  |  |  | 1.15.1
1.15.3 | Batch indicator calculation | Engine | P0 | ⬜ |  |  |  |  | 1.15.2
1.15.4 | Store in IndicatorValue table | Engine | P0 | ⬜ |  |  |  |  | 1.15.3
1.16.1 | Integration test: Full pipeline | Integration | P0 | ⬜ |  |  |  |  | 1.15.4
1.16.2 | NIFTY 24000 CE RSI test | Integration | P0 | ⬜ |  |  |  |  | 1.16.1 | < 0.5% vs TV
1.16.3 | Document all components | Docs | P1 | ⬜ |  |  |  |  | 1.16.2
1.16.4 | Phase 1 review & sign-off | Milestone | P0 | ⬜ |  |  |  |  | 1.16.3

## Phase 2 - Screener
PHASE 2: SCREENER ENGINE & UI (Weeks 5-8)
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
2.1.1 | Create screener/scanner.py | Scanner | P0 | ⬜ |  |  |  |  | -
2.1.2 | Implement Scanner class | Scanner | P0 | ⬜ |  |  |  |  | 2.1.1
2.1.3 | Define filter conditions | Scanner | P0 | ⬜ |  |  |  |  | 2.1.2
2.1.4 | Implement RSI > threshold | Scanner | P0 | ⬜ |  |  |  |  | 2.1.3
2.1.5 | Implement RSI < threshold | Scanner | P0 | ⬜ |  |  |  |  | 2.1.3
2.1.6 | Implement RSI crosses above | Scanner | P0 | ⬜ |  |  |  |  | 2.1.4
2.1.7 | Implement RSI crosses below | Scanner | P0 | ⬜ |  |  |  |  | 2.1.5
2.1.8 | Implement MACD conditions | Scanner | P0 | ⬜ |  |  |  |  | 2.1.6
2.1.9 | Implement EMA conditions | Scanner | P0 | ⬜ |  |  |  |  | 2.1.7
2.1.10 | Test: Single condition scan | Scanner | P1 | ⬜ |  |  |  |  | 2.1.9
2.2.1 | Implement multi-condition AND | Logic | P0 | ⬜ |  |  |  |  | 2.1.10
2.2.2 | Implement multi-condition OR | Logic | P0 | ⬜ |  |  |  |  | 2.1.10
2.2.3 | Implement condition groups | Logic | P1 | ⬜ |  |  |  |  | 2.2.2
2.2.4 | Test: Complex scan | Logic | P1 | ⬜ |  |  |  |  | 2.2.3
2.3.1 | Create screener/signals.py | Signals | P0 | ⬜ |  |  |  |  | 2.2.4
2.3.2 | Implement SignalDetector | Signals | P0 | ⬜ |  |  |  |  | 2.3.1
2.3.3 | Detect crossovers | Signals | P0 | ⬜ |  |  |  |  | 2.3.2
2.3.4 | Store historical values | Signals | P0 | ⬜ |  |  |  |  | 2.3.3
2.3.5 | Emit signal events | Signals | P0 | ⬜ |  |  |  |  | 2.3.4
2.3.6 | Save signals to DB | Signals | P0 | ⬜ |  |  |  |  | 2.3.5
2.4.1 | Create api/main.py | API | P0 | ⬜ |  |  |  |  | -
2.4.2 | Set up FastAPI app | API | P0 | ⬜ |  |  |  |  | 2.4.1
2.4.3 | Add CORS middleware | API | P0 | ⬜ |  |  |  |  | 2.4.2
2.4.4 | Create health endpoint | API | P0 | ⬜ |  |  |  |  | 2.4.3
2.4.5 | Create instruments endpoint | API | P0 | ⬜ |  |  |  |  | 2.4.4
2.4.6 | Create screeners CRUD | API | P0 | ⬜ |  |  |  |  | 2.4.5
2.4.7 | Create scan endpoint | API | P0 | ⬜ |  |  |  |  | 2.4.6
2.4.8 | Create results endpoint | API | P0 | ⬜ |  |  |  |  | 2.4.7
2.4.9 | Add request validation | API | P0 | ⬜ |  |  |  |  | 2.4.8
2.4.10 | Test all endpoints | API | P1 | ⬜ |  |  |  |  | 2.4.9
2.5.1 | Create frontend/web project | Frontend | P0 | ⬜ |  |  |  |  | - | npm create vite
2.5.2 | Install Tailwind CSS | Frontend | P0 | ⬜ |  |  |  |  | 2.5.1
2.5.3 | Install shadcn/ui | Frontend | P0 | ⬜ |  |  |  |  | 2.5.2
2.5.4 | Create layout component | Frontend | P0 | ⬜ |  |  |  |  | 2.5.3
2.5.5 | Create navigation | Frontend | P0 | ⬜ |  |  |  |  | 2.5.4
2.5.6 | Create screener builder UI | Frontend | P0 | ⬜ |  |  |  |  | 2.5.5
2.5.7 | Underlying selector | Frontend | P0 | ⬜ |  |  |  |  | 2.5.6
2.5.8 | Indicator selector | Frontend | P0 | ⬜ |  |  |  |  | 2.5.6
2.5.9 | Condition builder | Frontend | P0 | ⬜ |  |  |  |  | 2.5.8
2.5.10 | Timeframe selector | Frontend | P0 | ⬜ |  |  |  |  | 2.5.6
2.6.1 | Create results table | Results | P0 | ⬜ |  |  |  |  | 2.5.10
2.6.2 | Add sorting | Results | P1 | ⬜ |  |  |  |  | 2.6.1
2.6.3 | Add filtering | Results | P1 | ⬜ |  |  |  |  | 2.6.2
2.6.4 | Add pagination | Results | P1 | ⬜ |  |  |  |  | 2.6.3
2.6.5 | Real-time updates | Results | P0 | ⬜ |  |  |  |  | 2.6.4
2.7.1 | Install TradingView charts | Charts | P0 | ⬜ |  |  |  |  | 2.6.5
2.7.2 | Create chart component | Charts | P0 | ⬜ |  |  |  |  | 2.7.1
2.7.3 | Display strike candles | Charts | P0 | ⬜ |  |  |  |  | 2.7.2
2.7.4 | Overlay indicators | Charts | P0 | ⬜ |  |  |  |  | 2.7.3
2.7.5 | Click row → chart popup | Charts | P0 | ⬜ |  |  |  |  | 2.7.4
2.8.1 | Connect frontend to API | Integration | P0 | ⬜ |  |  |  |  | 2.7.5
2.8.2 | Test full workflow | Integration | P0 | ⬜ |  |  |  |  | 2.8.1
2.8.3 | Performance testing | Integration | P1 | ⬜ |  |  |  |  | 2.8.2
2.8.4 | Phase 2 review & sign-off | Milestone | P0 | ⬜ |  |  |  |  | 2.8.3

## Phase 3 - Options
PHASE 3: OPTIONS DATA & FILTERS (Weeks 9-12)
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
3.1 OPTIONS CHAIN DATA
3.1.1 | Design options_chain table schema | Database | P0 | ⬜ |  |  |  |  | - | CE/PE, expiry, strike
3.1.2 | Create options_chain migration | Database | P0 | ⬜ |  |  |  |  | 3.1.1
3.1.3 | Implement OptionsChainRepository | Backend | P0 | ⬜ |  |  |  |  | 3.1.2
3.1.4 | Fetch options chain from Angel One | Data | P0 | ⬜ |  |  |  |  | 3.1.3 | SmartAPI
3.1.5 | Parse and store options chain | Data | P0 | ⬜ |  |  |  |  | 3.1.4
3.1.6 | Schedule options chain refresh | Data | P0 | ⬜ |  |  |  |  | 3.1.5 | Every 3 min
3.1.7 | Create GET /options/chain endpoint | API | P0 | ⬜ |  |  |  |  | 3.1.6
3.1.8 | Test: Options chain accuracy | Testing | P1 | ⬜ |  |  |  |  | 3.1.7 | vs NSE website
3.2 STRIKE OHLCV DATA
3.2.1 | Design strike_candles table schema | Database | P0 | ⬜ |  |  |  |  | - | Per strike OHLCV
3.2.2 | Create strike_candles migration | Database | P0 | ⬜ |  |  |  |  | 3.2.1
3.2.3 | Map strike symbols to Angel tokens | Data | P0 | ⬜ |  |  |  |  | 3.2.2 | Scrip master
3.2.4 | Implement StrikeCandleRepository | Backend | P0 | ⬜ |  |  |  |  | 3.2.3
3.2.5 | Fetch historical candles per strike | Data | P0 | ⬜ |  |  |  |  | 3.2.4 | getCandleData API
3.2.6 | Build real-time candles from ticks | Data | P0 | ⬜ |  |  |  |  | 3.2.5 | WebSocket
3.2.7 | Store candles in TimescaleDB/Redis | Data | P0 | ⬜ |  |  |  |  | 3.2.6 | Hypertable
3.2.8 | Create GET /strikes/{symbol}/candles | API | P0 | ⬜ |  |  |  |  | 3.2.7
3.2.9 | Test: Strike candle accuracy | Testing | P1 | ⬜ |  |  |  |  | 3.2.8
3.3 GREEKS CALCULATION
3.3.1 | Install py_vollib or mibian | Setup | P0 | ⬜ |  |  |  |  | -
3.3.2 | Create GreeksCalculator service | Backend | P0 | ⬜ |  |  |  |  | 3.3.1
3.3.3 | Implement IV calculation | Backend | P0 | ⬜ |  |  |  |  | 3.3.2 | Black-Scholes
3.3.4 | Implement Delta calculation | Backend | P0 | ⬜ |  |  |  |  | 3.3.3
3.3.5 | Implement Gamma calculation | Backend | P0 | ⬜ |  |  |  |  | 3.3.4
3.3.6 | Implement Theta calculation | Backend | P0 | ⬜ |  |  |  |  | 3.3.5
3.3.7 | Implement Vega calculation | Backend | P0 | ⬜ |  |  |  |  | 3.3.6
3.3.8 | Implement Rho calculation | Backend | P1 | ⬜ |  |  |  |  | 3.3.7
3.3.9 | Calculate Greeks for all strikes | Backend | P0 | ⬜ |  |  |  |  | 3.3.8 | Batch job
3.3.10 | Store Greeks in strike_greeks table | Database | P0 | ⬜ |  |  |  |  | 3.3.9
3.3.11 | Create GET /strikes/{symbol}/greeks | API | P0 | ⬜ |  |  |  |  | 3.3.10
3.3.12 | Test: Greeks vs broker values | Testing | P1 | ⬜ |  |  |  |  | 3.3.11
3.4 OPEN INTEREST & VOLUME
3.4.1 | Design oi_history table | Database | P0 | ⬜ |  |  |  |  | -
3.4.2 | Track OI changes over time | Data | P0 | ⬜ |  |  |  |  | 3.4.1
3.4.3 | Calculate OI change percentage | Backend | P0 | ⬜ |  |  |  |  | 3.4.2
3.4.4 | Calculate Put/Call ratio | Backend | P0 | ⬜ |  |  |  |  | 3.4.3
3.4.5 | Detect unusual OI spikes | Backend | P0 | ⬜ |  |  |  |  | 3.4.4 | Anomaly detection
3.4.6 | Create OI heatmap data endpoint | API | P0 | ⬜ |  |  |  |  | 3.4.5
3.4.7 | Test: OI tracking accuracy | Testing | P1 | ⬜ |  |  |  |  | 3.4.6
3.5 OPTIONS FILTERS
3.5.1 | Add IV filter to screener | Backend | P0 | ⬜ |  |  |  |  | 3.3.11 | IV > X%
3.5.2 | Add Delta filter to screener | Backend | P0 | ⬜ |  |  |  |  | 3.5.1
3.5.3 | Add Gamma filter to screener | Backend | P0 | ⬜ |  |  |  |  | 3.5.2
3.5.4 | Add OI filter to screener | Backend | P0 | ⬜ |  |  |  |  | 3.5.3 | OI > X
3.5.5 | Add OI change filter | Backend | P0 | ⬜ |  |  |  |  | 3.5.4 | OI change > X%
3.5.6 | Add volume filter | Backend | P0 | ⬜ |  |  |  |  | 3.5.5
3.5.7 | Add moneyness filter | Backend | P0 | ⬜ |  |  |  |  | 3.5.6 | ITM/ATM/OTM
3.5.8 | Add expiry filter | Backend | P0 | ⬜ |  |  |  |  | 3.5.7 | Near/next/far
3.5.9 | Combine with technical filters | Backend | P0 | ⬜ |  |  |  |  | 3.5.8 | AND/OR logic
3.5.10 | Test: Options filter combinations | Testing | P1 | ⬜ |  |  |  |  | 3.5.9
3.6 FRONTEND OPTIONS UI
3.6.1 | Create options chain view | Frontend | P0 | ⬜ |  |  |  |  | 3.4.6 | Table layout
3.6.2 | Display Greeks columns | Frontend | P0 | ⬜ |  |  |  |  | 3.6.1
3.6.3 | Add IV column with color coding | Frontend | P0 | ⬜ |  |  |  |  | 3.6.2
3.6.4 | Create OI heatmap component | Frontend | P1 | ⬜ |  |  |  |  | 3.6.3
3.6.5 | Add options filter controls | Frontend | P0 | ⬜ |  |  |  |  | 3.6.4
3.6.6 | Display strike chart on click | Frontend | P0 | ⬜ |  |  |  |  | 3.6.5 | TradingView
3.6.7 | Test: Options UI responsiveness | Testing | P1 | ⬜ |  |  |  |  | 3.6.6
3.7 INTEGRATION & MILESTONE
3.7.1 | Integration test: Full options flow | Testing | P0 | ⬜ |  |  |  |  | 3.6.7
3.7.2 | Performance test: 48K strikes | Testing | P0 | ⬜ |  |  |  |  | 3.7.1
3.7.3 | Documentation: Options features | Docs | P1 | ⬜ |  |  |  |  | 3.7.2
3.7.4 | Phase 3 review & sign-off | Milestone | P0 | ⬜ |  |  |  |  | 3.7.3

## Phase 4 - Users
PHASE 4: USER SYSTEM (Weeks 13-16)
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
4.1 AUTHENTICATION
4.1.1 | Set up Clerk account | Setup | P0 | ⬜ |  |  |  |  | - | clerk.com
4.1.2 | Install Clerk SDK (frontend) | Setup | P0 | ⬜ |  |  |  |  | 4.1.1
4.1.3 | Configure Clerk environment vars | Setup | P0 | ⬜ |  |  |  |  | 4.1.2
4.1.4 | Create sign-in page | Frontend | P0 | ⬜ |  |  |  |  | 4.1.3
4.1.5 | Create sign-up page | Frontend | P0 | ⬜ |  |  |  |  | 4.1.4
4.1.6 | Implement protected routes | Frontend | P0 | ⬜ |  |  |  |  | 4.1.5
4.1.7 | Add Clerk middleware (backend) | Backend | P0 | ⬜ |  |  |  |  | 4.1.6 | JWKS validation
4.1.8 | Create user on first login | Backend | P0 | ⬜ |  |  |  |  | 4.1.7
4.1.9 | Test: Auth flow end-to-end | Testing | P1 | ⬜ |  |  |  |  | 4.1.8
4.2 USER DATABASE
4.2.1 | Design users table schema | Database | P0 | ⬜ |  |  |  |  | - | clerk_user_id
4.2.2 | Create users migration | Database | P0 | ⬜ |  |  |  |  | 4.2.1
4.2.3 | Design user_preferences table | Database | P0 | ⬜ |  |  |  |  | 4.2.2
4.2.4 | Create preferences migration | Database | P0 | ⬜ |  |  |  |  | 4.2.3
4.2.5 | Implement UserRepository | Backend | P0 | ⬜ |  |  |  |  | 4.2.4
4.2.6 | Implement PreferencesRepository | Backend | P0 | ⬜ |  |  |  |  | 4.2.5
4.2.7 | Create GET /api/user endpoint | API | P0 | ⬜ |  |  |  |  | 4.2.6
4.2.8 | Create PUT /api/user endpoint | API | P0 | ⬜ |  |  |  |  | 4.2.7
4.2.9 | Test: User CRUD operations | Testing | P1 | ⬜ |  |  |  |  | 4.2.8
4.3 SAVED SCREENERS
4.3.1 | Design saved_screeners table | Database | P0 | ⬜ |  |  |  |  | -
4.3.2 | Create saved_screeners migration | Database | P0 | ⬜ |  |  |  |  | 4.3.1
4.3.3 | Implement ScreenerRepository | Backend | P0 | ⬜ |  |  |  |  | 4.3.2
4.3.4 | Create POST /screeners (save) | API | P0 | ⬜ |  |  |  |  | 4.3.3
4.3.5 | Create GET /screeners (list) | API | P0 | ⬜ |  |  |  |  | 4.3.4
4.3.6 | Create GET /screeners/{id} | API | P0 | ⬜ |  |  |  |  | 4.3.5
4.3.7 | Create PUT /screeners/{id} | API | P0 | ⬜ |  |  |  |  | 4.3.6
4.3.8 | Create DELETE /screeners/{id} | API | P0 | ⬜ |  |  |  |  | 4.3.7
4.3.9 | Add save button to screener UI | Frontend | P0 | ⬜ |  |  |  |  | 4.3.8
4.3.10 | Create saved screeners list page | Frontend | P0 | ⬜ |  |  |  |  | 4.3.9
4.3.11 | Load saved screener on click | Frontend | P0 | ⬜ |  |  |  |  | 4.3.10
4.3.12 | Test: Saved screeners flow | Testing | P1 | ⬜ |  |  |  |  | 4.3.11
4.4 WATCHLISTS
4.4.1 | Design watchlists table | Database | P0 | ⬜ |  |  |  |  | -
4.4.2 | Design watchlist_items table | Database | P0 | ⬜ |  |  |  |  | 4.4.1
4.4.3 | Create watchlist migrations | Database | P0 | ⬜ |  |  |  |  | 4.4.2
4.4.4 | Implement WatchlistRepository | Backend | P0 | ⬜ |  |  |  |  | 4.4.3
4.4.5 | Create watchlist CRUD endpoints | API | P0 | ⬜ |  |  |  |  | 4.4.4
4.4.6 | Add to watchlist from results | Frontend | P0 | ⬜ |  |  |  |  | 4.4.5
4.4.7 | Create watchlist page | Frontend | P0 | ⬜ |  |  |  |  | 4.4.6
4.4.8 | Real-time watchlist updates | Frontend | P0 | ⬜ |  |  |  |  | 4.4.7 | WebSocket
4.4.9 | Test: Watchlist functionality | Testing | P1 | ⬜ |  |  |  |  | 4.4.8
4.5 ALERTS
4.5.1 | Design alerts table schema | Database | P0 | ⬜ |  |  |  |  | -
4.5.2 | Create alerts migration | Database | P0 | ⬜ |  |  |  |  | 4.5.1
4.5.3 | Implement AlertRepository | Backend | P0 | ⬜ |  |  |  |  | 4.5.2
4.5.4 | Create alert CRUD endpoints | API | P0 | ⬜ |  |  |  |  | 4.5.3
4.5.5 | Implement alert evaluation engine | Backend | P0 | ⬜ |  |  |  |  | 4.5.4
4.5.6 | Integrate with screener engine | Backend | P0 | ⬜ |  |  |  |  | 4.5.5
4.5.7 | Send push notifications | Backend | P1 | ⬜ |  |  |  |  | 4.5.6 | Firebase
4.5.8 | Send email notifications | Backend | P1 | ⬜ |  |  |  |  | 4.5.7 | SES
4.5.9 | Create alerts management UI | Frontend | P0 | ⬜ |  |  |  |  | 4.5.8
4.5.10 | Test: Alert triggering | Testing | P1 | ⬜ |  |  |  |  | 4.5.9
4.6 USER PREFERENCES
4.6.1 | Create preferences page | Frontend | P0 | ⬜ |  |  |  |  | 4.2.9
4.6.2 | Default timeframe setting | Frontend | P0 | ⬜ |  |  |  |  | 4.6.1
4.6.3 | Default indicator settings | Frontend | P0 | ⬜ |  |  |  |  | 4.6.2
4.6.4 | Theme preference (dark/light) | Frontend | P1 | ⬜ |  |  |  |  | 4.6.3
4.6.5 | Notification preferences | Frontend | P0 | ⬜ |  |  |  |  | 4.6.4
4.6.6 | Persist preferences to backend | Backend | P0 | ⬜ |  |  |  |  | 4.6.5
4.6.7 | Test: Preferences persistence | Testing | P1 | ⬜ |  |  |  |  | 4.6.6
4.7 INTEGRATION & MILESTONE
4.7.1 | Integration test: User journey | Testing | P0 | ⬜ |  |  |  |  | 4.6.7
4.7.2 | Security audit: Auth & data | Testing | P0 | ⬜ |  |  |  |  | 4.7.1
4.7.3 | Documentation: User features | Docs | P1 | ⬜ |  |  |  |  | 4.7.2
4.7.4 | Phase 4 review & sign-off | Milestone | P0 | ⬜ |  |  |  |  | 4.7.3

## Phase 5 - AI Agents
PHASE 5: AI AGENTS (Weeks 17-22)
ID | Task | Category | Priority | Status | Assigned To | Start Date | Due Date | Completed Date | Dependencies | Notes | Blockers
5.1.1 | Create agents/orchestrator/agent.py | Orchestrator | P0 | ⬜ |  |  |  |  | -
5.1.2 | Implement OrchestratorAgent | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.1
5.1.3 | Define workflow registry | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.2
5.1.4 | Implement SCAN workflow | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.3
5.1.5 | Implement BACKTEST workflow | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.3
5.1.6 | Implement ANALYZE workflow | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.3
5.1.7 | Parallel agent execution | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.6
5.1.8 | Error handling | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.7
5.1.9 | Job status tracking | Orchestrator | P0 | ⬜ |  |  |  |  | 5.1.8
5.1.10 | Test: Basic workflow | Orchestrator | P1 | ⬜ |  |  |  |  | 5.1.9
5.2.1 | Create agents/tagger/agent.py | Tagger | P0 | ⬜ |  |  |  |  | -
5.2.2 | Implement StrikeTaggerAgent | Tagger | P0 | ⬜ |  |  |  |  | 5.2.1
5.2.3 | Define output schema | Tagger | P0 | ⬜ |  |  |  |  | 5.2.2 | Pydantic
5.2.4 | Calculate moneyness | Tagger | P0 | ⬜ |  |  |  |  | 5.2.3 | ITM/ATM/OTM
5.2.5 | Calculate liquidity score | Tagger | P0 | ⬜ |  |  |  |  | 5.2.4
5.2.6 | Update instruments DB | Tagger | P0 | ⬜ |  |  |  |  | 5.2.5
5.2.7 | Test: Tag NIFTY strikes | Tagger | P1 | ⬜ |  |  |  |  | 5.2.6
5.3.1 | Create agents/greeks/agent.py | Greeks | P0 | ⬜ |  |  |  |  | -
5.3.2 | Implement GreeksAgent | Greeks | P0 | ⬜ |  |  |  |  | 5.3.1
5.3.3 | Implement IV calculation | Greeks | P0 | ⬜ |  |  |  |  | 5.3.2 | Black-Scholes
5.3.4 | Implement Delta | Greeks | P0 | ⬜ |  |  |  |  | 5.3.3
5.3.5 | Implement Gamma | Greeks | P0 | ⬜ |  |  |  |  | 5.3.4
5.3.6 | Implement Theta | Greeks | P0 | ⬜ |  |  |  |  | 5.3.5
5.3.7 | Implement Vega | Greeks | P0 | ⬜ |  |  |  |  | 5.3.6
5.3.8 | Store in IndicatorValue | Greeks | P0 | ⬜ |  |  |  |  | 5.3.7
5.3.9 | Test: Validate Greeks | Greeks | P1 | ⬜ |  |  |  |  | 5.3.8 | vs NSE
5.4.1 | Create agents/scanner/agent.py | Scanner | P0 | ⬜ |  |  |  |  | 5.1.10
5.4.2 | Implement SignalScannerAgent | Scanner | P0 | ⬜ |  |  |  |  | 5.4.1
5.4.3 | Batch processing | Scanner | P0 | ⬜ |  |  |  |  | 5.4.2 | 48k+ strikes
5.4.4 | Parallel indicator calc | Scanner | P0 | ⬜ |  |  |  |  | 5.4.3
5.4.5 | Filter by conditions | Scanner | P0 | ⬜ |  |  |  |  | 5.4.4
5.4.6 | Return matched strikes | Scanner | P0 | ⬜ |  |  |  |  | 5.4.5
5.4.7 | Test: Scan all NIFTY | Scanner | P1 | ⬜ |  |  |  |  | 5.4.6
5.5.1 | Create agents/researcher/agent.py | Researcher | P0 | ⬜ |  |  |  |  | -
5.5.2 | Implement ResearcherAgent | Researcher | P0 | ⬜ |  |  |  |  | 5.5.1
5.5.3 | Web scraping tools | Researcher | P0 | ⬜ |  |  |  |  | 5.5.2
5.5.4 | News API integration | Researcher | P1 | ⬜ |  |  |  |  | 5.5.3
5.5.5 | FII/DII data fetch | Researcher | P0 | ⬜ |  |  |  |  | 5.5.3
5.5.6 | Unusual OI detection | Researcher | P0 | ⬜ |  |  |  |  | 5.5.5
5.5.7 | Store in ChromaDB | Researcher | P0 | ⬜ |  |  |  |  | 5.5.6
5.5.8 | Schedule every 2 hours | Researcher | P0 | ⬜ |  |  |  |  | 5.5.7
5.6.1 | Create agents/sentiment/agent.py | Sentiment | P0 | ⬜ |  |  |  |  | -
5.6.2 | Implement SentimentAgent | Sentiment | P0 | ⬜ |  |  |  |  | 5.6.1
5.6.3 | MoneyControl scraper | Sentiment | P1 | ⬜ |  |  |  |  | 5.6.2
5.6.4 | Sentiment classification | Sentiment | P0 | ⬜ |  |  |  |  | 5.6.3 | Ollama
5.6.5 | Score aggregation | Sentiment | P0 | ⬜ |  |  |  |  | 5.6.4
5.6.6 | Schedule every 30 min | Sentiment | P0 | ⬜ |  |  |  |  | 5.6.5
5.7.1 | Create agents/reporter/agent.py | Reporter | P0 | ⬜ |  |  |  |  | 5.6.6
5.7.2 | Implement ReporterAgent | Reporter | P0 | ⬜ |  |  |  |  | 5.7.1
5.7.3 | Define report template | Reporter | P0 | ⬜ |  |  |  |  | 5.7.2 | Markdown
5.7.4 | Compile agent outputs | Reporter | P0 | ⬜ |  |  |  |  | 5.7.3
5.7.5 | Generate summary | Reporter | P0 | ⬜ |  |  |  |  | 5.7.4 | Ollama
5.7.6 | Save to job record | Reporter | P0 | ⬜ |  |  |  |  | 5.7.5
5.8.1 | Create agents/backtester/agent.py | Backtester | P0 | ⬜ |  |  |  |  | -
5.8.2 | Implement BacktesterAgent | Backtester | P0 | ⬜ |  |  |  |  | 5.8.1
5.8.3 | Historical data loader | Backtester | P0 | ⬜ |  |  |  |  | 5.8.2
5.8.4 | Entry/exit logic | Backtester | P0 | ⬜ |  |  |  |  | 5.8.3
5.8.5 | P&L calculation | Backtester | P0 | ⬜ |  |  |  |  | 5.8.4
5.8.6 | Sharpe ratio | Backtester | P0 | ⬜ |  |  |  |  | 5.8.5
5.8.7 | Max drawdown | Backtester | P0 | ⬜ |  |  |  |  | 5.8.6
5.8.8 | Win rate | Backtester | P0 | ⬜ |  |  |  |  | 5.8.7
5.8.9 | Generate report | Backtester | P0 | ⬜ |  |  |  |  | 5.8.8
5.9.1 | Create agents/optimizer/agent.py | Optimizer | P0 | ⬜ |  |  |  |  | 5.8.9
5.9.2 | Implement OptimizerAgent | Optimizer | P0 | ⬜ |  |  |  |  | 5.9.1
5.9.3 | Grid search | Optimizer | P0 | ⬜ |  |  |  |  | 5.9.2
5.9.4 | Walk-forward analysis | Optimizer | P1 | ⬜ |  |  |  |  | 5.9.3
5.9.5 | Best params selection | Optimizer | P0 | ⬜ |  |  |  |  | 5.9.4
5.10.1 | Create agents/analyzer/agent.py | Analyzer | P0 | ⬜ |  |  |  |  | -
5.10.2 | Implement OptionsAnalyzer | Analyzer | P0 | ⬜ |  |  |  |  | 5.10.1
5.10.3 | Strike selection logic | Analyzer | P0 | ⬜ |  |  |  |  | 5.10.2
5.10.4 | Payoff diagram calc | Analyzer | P0 | ⬜ |  |  |  |  | 5.10.3
5.10.5 | Risk/reward analysis | Analyzer | P0 | ⬜ |  |  |  |  | 5.10.4
5.11.1 | Create agents/risk/agent.py | Risk | P0 | ⬜ |  |  |  |  | 5.10.5
5.11.2 | Implement RiskAgent | Risk | P0 | ⬜ |  |  |  |  | 5.11.1
5.11.3 | Portfolio Greeks sum | Risk | P0 | ⬜ |  |  |  |  | 5.11.2
5.11.4 | VaR calculation | Risk | P1 | ⬜ |  |  |  |  | 5.11.3
5.11.5 | Hedging suggestions | Risk | P1 | ⬜ |  |  |  |  | 5.11.4
5.12.1 | Integration test: SCAN | Integration | P0 | ⬜ |  |  |  |  | 5.11.5
5.12.2 | Integration test: BACKTEST | Integration | P0 | ⬜ |  |  |  |  | 5.12.1
5.12.3 | Integration test: ANALYZE | Integration | P0 | ⬜ |  |  |  |  | 5.12.2
5.12.4 | Performance benchmarks | Integration | P1 | ⬜ |  |  |  |  | 5.12.3
5.12.5 | Phase 5 review & sign-off | Milestone | P0 | ⬜ |  |  |  |  | 5.12.4

## Risk Register
RISK REGISTER
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status | Last Updated
R001 | Angel One API rate limits exceeded | Technical | Medium | High |  | Implement caching, request throttling |  | Open
R002 | Angel One API changes without notice | External | Low | High |  | Version lock API client, monitor changelogs |  | Open
R003 | Ollama model performance insufficient | Technical | Medium | Medium |  | Test multiple models, have Bedrock fallback |  | Open
R004 | Data quality issues from Angel One | Data | Medium | High |  | Validation layer, compare with NSE data |  | Open
R005 | Indicator calculations differ from TradingView | Technical | High | Medium |  | Extensive validation, document methodology |  | Open
R006 | Scope creep / feature bloat | Project | High | High |  | Strict phase gates, MVP focus |  | Open
R007 | Single developer bandwidth | Resource | High | Medium |  | Prioritize ruthlessly, use AI assistance |  | Open
R008 | Production AWS costs exceed budget | Financial | Medium | Medium |  | Cost alerts, serverless architecture |  | Open
R009 | WebSocket connection instability | Technical | Medium | High |  | Reconnection logic, heartbeat monitoring |  | Open
R010 | Market data gaps during high volatility | External | Medium | High |  | Gap detection, data reconciliation |  | Open

## Weekly Standup
WEEKLY STANDUP LOG
Week # | Date | Completed This Week | In Progress | Blockers | Next Week Goals
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16
Week 17
Week 18
Week 19
Week 20
Week 21
Week 22
Week 23
Week 24
Week 25
Week 26
Week 27
Week 28
Week 29
Week 30

## Decisions Log
ARCHITECTURAL DECISIONS LOG
ID | Date | Decision | Context | Options Considered | Rationale | Status
ADR001 |  | Use SQLite for local development | Need simple database without Docker | SQLite, PostgreSQL local, DuckDB | Zero config, Python built-in, good enough for dev | Approved
ADR002 |  | Use Ollama for local LLM | Need free local AI without API costs | Ollama, LM Studio, llama.cpp | Best UX, easy model management, good performance | Approved
ADR003 |  | Use file-based cache instead of Redis | Cannot run Docker/Redis locally | File cache, SQLite cache, in-memory | Simple, persistent, easy to migrate to Redis | Approved
ADR004 |  | Use ChromaDB for local vectors | Need vector DB without cloud dependency | ChromaDB, Qdrant, FAISS | Embedded, persistent, good Python integration | Approved
ADR005 |  | Use Angel One SmartAPI | Need Indian market options data | Angel One, Zerodha Kite, Upstox | Free historical data, user already has account | Approved

## Testing Matrix
TESTING MATRIX
Component | Unit Tests | Integration Tests | Manual Tests | Coverage % | Last Run | Status | Notes
Database Models | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
File Cache | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Angel One Auth | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Scrip Master | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Candle Fetcher | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
WebSocket Client | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Candle Builder | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
RSI Indicator | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started | Must validate vs TV
MACD Indicator | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Scanner Engine | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Signal Detector | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
FastAPI Endpoints | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Orchestrator Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Tagger Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Greeks Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Scanner Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Researcher Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started
Backtester Agent | ⬜ | ⬜ | ⬜ | 0% |  | ⬜ Not Started

## Production Checklist
PRODUCTION READINESS CHECKLIST
Category | Item | Status | Verified By | Date
Security | API keys in Secrets Manager | ⬜
Security | HTTPS enabled | ⬜
Security | CORS configured | ⬜
Security | Input validation | ⬜
Security | Rate limiting | ⬜
Security | JWT auth implemented | ⬜
Performance | Database indexes optimized | ⬜
Performance | Cache strategy implemented | ⬜
Performance | CDN configured | ⬜
Performance | Load testing passed | ⬜
Monitoring | CloudWatch alarms set | ⬜
Monitoring | Error tracking configured | ⬜
Monitoring | Health checks enabled | ⬜
Monitoring | Log retention configured | ⬜
Reliability | Auto-scaling configured | ⬜
Reliability | Dead letter queues set | ⬜
Reliability | Retry logic implemented | ⬜
Reliability | Graceful degradation | ⬜
Data | Backup strategy defined | ⬜
Data | Data retention policy | ⬜
Data | GDPR compliance checked | ⬜
Documentation | API documentation complete | ⬜
Documentation | Runbook created | ⬜
Documentation | Architecture diagram updated | ⬜
Testing | All unit tests passing | ⬜
Testing | Integration tests passing | ⬜
Testing | UAT sign-off received | ⬜