## Rollout Checklist
StrikeEdge Rollout Execution Checklist
Generated: 2026-03-08 15:03
Step | Environment | Task | Status | Completed By | Timestamp | Notes
PRE-FLIGHT CHECKS
1.1 | Local | Backend pytest tests pass (python -m pytest tests -q) | ☐ Pending
1.2 | Local | Uvicorn server starts (uvicorn app.main:app --port 8000) | ☐ Pending
1.3 | Local | Health check passes (post_deploy_health_check.py --base-url http://localhost:8000) | ☐ Pending
1.4 | Local | Load test smoke passes (load_test_smoke.py --base-url http://localhost:8000) | ☐ Pending
BROKER AUTH & INGESTION
2.1 | Local | WebSocket ingestion starts (run_ws_ingest.py) | ☐ Pending
2.2 | Local | No TOTP/auth errors in logs | ☐ Pending
2.3 | Local | Tick ingestion logs appear | ☐ Pending
2.4 | Local | /ready endpoint remains healthy during ingestion | ☐ Pending
TERRAFORM SETUP
3.1 | Local | Set TF_VAR_db_master_password env variable | ☐ Pending
3.2 | Local | AWS credentials/profile active in shell | ☐ Pending
3.3 | Local | Terraform init successful | ☐ Pending
DEV ENVIRONMENT
4.1 | Dev | Terraform plan successful (release_orchestrator.py --env dev) | ☐ Pending
4.2 | Dev | Terraform apply successful (--apply flag) | ☐ Pending
4.3 | Dev | post_deploy_health_check.py passes | ☐ Pending
4.4 | Dev | load_test_smoke.py passes | ☐ Pending
4.5 | Dev | No broker auth/ingestion failures | ☐ Pending
4.6 | Dev | Manual smoke test completed | ☐ Pending
STAGING ENVIRONMENT
5.1 | Staging | Terraform plan successful (release_orchestrator.py --env staging) | ☐ Pending
5.2 | Staging | Terraform apply successful (--apply flag) | ☐ Pending
5.3 | Staging | post_deploy_health_check.py passes | ☐ Pending
5.4 | Staging | load_test_smoke.py passes | ☐ Pending
5.5 | Staging | No broker auth/ingestion failures | ☐ Pending
5.6 | Staging | Integration tests pass | ☐ Pending
PREPROD ENVIRONMENT
6.1 | Preprod | Terraform plan successful (release_orchestrator.py --env preprod) | ☐ Pending
6.2 | Preprod | Terraform apply successful (--apply flag) | ☐ Pending
6.3 | Preprod | post_deploy_health_check.py passes | ☐ Pending
6.4 | Preprod | load_test_smoke.py passes | ☐ Pending
6.5 | Preprod | No broker auth/ingestion failures | ☐ Pending
6.6 | Preprod | Performance baseline captured | ☐ Pending
PROD ENVIRONMENT (STRICT)
7.1 | Prod | Change approval obtained | ☐ Pending
7.2 | Prod | Rollback plan reviewed | ☐ Pending
7.3 | Prod | Terraform plan successful (release_orchestrator.py --env prod) | ☐ Pending
7.4 | Prod | Terraform apply successful (--apply flag) | ☐ Pending
7.5 | Prod | post_deploy_health_check.py passes | ☐ Pending
7.6 | Prod | load_test_smoke.py passes | ☐ Pending
7.7 | Prod | No broker auth/ingestion failures | ☐ Pending
7.8 | Prod | Production verification complete | ☐ Pending
ROLLBACK READINESS (PROD)
8.1 | Prod | List existing snapshots (aws_db_snapshot.py --cluster-id strikeedge-prod-aurora list) | ☐ Pending
8.2 | Prod | Create pre-deploy snapshot | ☐ Pending
8.3 | Prod | Verify snapshot available | ☐ Pending
8.4 | Prod | Document rollback procedure | ☐ Pending
CI/CD VERIFICATION (OPTIONAL)
9.1 | Dev | GitHub workflow post-deploy-health passes | ☐ Pending
9.2 | Staging | GitHub workflow post-deploy-health passes | ☐ Pending
9.3 | Preprod | GitHub workflow post-deploy-health passes | ☐ Pending
9.4 | Prod | GitHub workflow post-deploy-health passes | ☐ Pending
Status Legend:
☐ Pending
✓ Passed
✗ Failed

## Environment URLs
Environment Configuration
Environment | API Base URL | Cluster ID | Notes
Local | http://localhost:8000 | N/A | Local development
Dev | <DEV_API_URL> | strikeedge-dev-aurora | Development environment
Staging | <STAGING_API_URL> | strikeedge-staging-aurora | Staging environment
Preprod | <PREPROD_API_URL> | strikeedge-preprod-aurora | Pre-production
Prod | <PROD_API_URL> | strikeedge-prod-aurora | Production - STRICT

## Command Reference
Quick Command Reference
Task | Command | Description
LOCAL TESTING
Backend Tests | cd backend && python -m pytest tests -q | Run unit tests
Start Server | uvicorn app.main:app --host 0.0.0.0 --port 8000 | Start local API
Health Check | python scripts/post_deploy_health_check.py --base-url http://localhost:8000 | Verify API health
Load Test | python scripts/load_test_smoke.py --base-url http://localhost:8000 | Run smoke load test
WS Ingestion | python scripts/run_ws_ingest.py | Test broker WebSocket
TERRAFORM
Set Password | $env:TF_VAR_db_master_password="<password>" | Windows PowerShell
Set Password | export TF_VAR_db_master_password="<password>" | Linux/Mac
RELEASE ORCHESTRATOR
Dev Plan | python scripts/release_orchestrator.py --env dev --base-url <URL> | Plan only
Dev Apply | python scripts/release_orchestrator.py --env dev --base-url <URL> --apply | Plan + Apply
Staging Plan | python scripts/release_orchestrator.py --env staging --base-url <URL> | Plan only
Staging Apply | python scripts/release_orchestrator.py --env staging --base-url <URL> --apply | Plan + Apply
Preprod Plan | python scripts/release_orchestrator.py --env preprod --base-url <URL> | Plan only
Preprod Apply | python scripts/release_orchestrator.py --env preprod --base-url <URL> --apply | Plan + Apply
Prod Plan | python scripts/release_orchestrator.py --env prod --base-url <URL> | Plan only
Prod Apply | python scripts/release_orchestrator.py --env prod --base-url <URL> --apply | Plan + Apply
DATABASE SNAPSHOTS
List Snapshots | python scripts/aws_db_snapshot.py --cluster-id <cluster> list | View existing
Create Snapshot | python scripts/aws_db_snapshot.py --cluster-id <cluster> create | Dry run
Create (Execute) | python scripts/aws_db_snapshot.py --cluster-id <cluster> create --execute | Actually create

## Execution Log
Deployment Execution Log
Timestamp | Environment | Action | Result | Details/Errors